## Time Line
Little Helpers Time Line
Task | Assign To | Estimated Hours | Start Date | End Date
Database Design Undertstanding | Shayan,Mazz,Hassan,Usman | 3 | 2023-04-27 | 2023-04-27
Screens Designing and Approval of Task Management and Project Management on Figma | Irfan ,Wasi | 10 | 2023-04-26 | 2023-04-27
Database Sps of Task Management and Project Management | Shayan,Mazz,Hassan,Usman | 13 | 2023-04-27 | 2023-04-28
Conversion of Figma Design to HTML and CSS | Iftikhar | 8 | 2023-04-28 | 2023-04-28
Project Setup List | Hassan | 8 | 2023-05-02 | 2023-05-02
Project Setup Crud | Hassan | 24 | 2023-05-03 | 2023-05-05
Project Approval Cycle | Hassan | 8 | 2023-05-08 | 2023-05-08
Module Setup List | Shayan | 8 | 2023-05-02 | 2023-05-02
Module Setup Crud | Shayan | 8 | 2023-05-03 | 2023-05-03
Task Listing | Maaz | 4 | 2023-05-02 | 2023-05-02
Task Crud | Maaz | 24 | 2023-05-02 | 2023-05-05
Task Approval | Maaz | 4 | 2023-05-05 | 2023-05-05
Task Assigning Screen | Maaz | 4 | 2023-05-08 | 2023-05-08
Task Assigning Approval | Maaz | 4 | 2023-05-08 | 2023-05-08
Product Listing | Shayan | 8 | 2023-05-04 | 2023-05-04
Product Crud Screen | Shayan | 8 | 2023-05-05 | 2023-05-05
Testing Of Project Setup | Usman | 4 | 2023-05-08 | 2023-05-08
Testing Of Module Setup | Usman | 2 | 2023-05-09 | 2023-05-09
Testing Of Product Setup | Usman | 2 | 2023-05-09 | 2023-05-09
Testing Of Task Management | Usman | 4 | 2023-05-09 | 2023-05-09
Bugs resolution of Project Setup | Hassan | 4 | 2023-05-09 | 2023-05-09
Bugs resolution of Module and Product Setup | Shayan | 4 | 2023-05-09 | 2023-05-09
Bugs Resolution of Task Management | Maaz | 4 | 2023-05-09 | 2023-05-09
Reward Management DB Design and SPs | Usman | 4 | 2023-05-03 | 2023-05-03
Blogs Posting and NewsLetter Postion DB Design and SPS | Usman | 4 | 2023-05-03 | 2023-05-03
Incident Reporting DB Design and Sps | Usman | 4 | 2023-05-04 | 2023-05-04
Inventory Management partially Pending Db design and Sps | Usman | 12 | 2023-05-04 | 2023-05-05
Incident Reporting , Blog ,News Letter ,Badges, Reward Setup and Report HTML | Iftikhar | 24 | 2023-05-02 | 2023-05-04
Inventory Management Screens Figma TO Html | Iftikhar | 24 | 2023-05-05 | 2023-05-09
Website Front Design Figma V1 | Iftikhar | 8 | 2023-05-10 | 2023-05-10
Website Front Design Figma V2 | Iftikhar | 5 | 2023-05-11 | 2023-05-11
Website Front Design Figma V3 | Iftikhar | 5 | 2023-05-11 | 2023-05-12
Reward Setup Listing | Shayan | 8 | 2023-05-09 | 2023-05-10
Reward Setup Crud | Shayan | 8 | 2023-05-10 | 2023-05-11
Badges Listing | Shayan | 4 | 2023-05-11 | 2023-05-11
Badges Crud | Shayan | 4 | 2023-05-12 | 2023-05-12
Reward Crud and Listing Testing | Usman | 2 | 2023-05-11 | 2023-05-11
Reward Bugs Fixing | Shayan and Usman | 2 | 2023-05-12 | 2023-05-12
Badges Crud and Listing Testing | Usman | 2 | 2023-05-13 | 2023-05-13
Blog and Newsletter Posting Listing | Maaz | 8 | 2023-05-09 | 2023-05-10
Blog and Newsletter Posting Crud Screen | Maaz | 8 | 2023-05-10 | 2023-05-11
Blog and Newsletter Posting Approval Cycle | Maaz | 8 | 2023-05-11 | 2023-05-12
Blog and Newsltter Posting Testing | Usman | 4 | 2023-05-13 | 2023-05-13
Incident Reporting Listing | Hassan | 4 | 2023-05-09 | 2023-05-09
Incident reporting crud | Hassan | 8 | 2023-05-10 | 2023-05-10
Incident Reporting Approval Cycle | Hassan | 8 | 2023-05-11 | 2023-05-11
Incident Reporting Testing | Usman | 3 | 2023-05-13 | 2023-05-13
Badges Bug Fixing and Testing | Shayan and Usman | 2 | 2023-05-15 | 2023-05-15
Blog and Newsltter Posting Bug Fixing and Testing | Maaz and Usman | 4 | 2023-05-15 | 2023-05-15
Incident Reporting Bug Fixing and Testing | Hassan and Usman | 2 | 2023-05-15 | 2023-05-15